## Slide 1: Active Lane Centering Status Update
A nshuman Singh
D avide Occello
R A ymond Wouters
S harad Bhadgaonkar, February 09th 2017

## Slide 2: Agenda
Team Update
Project Timeline
Status from the last lesson
Planning for next phase
Scope limitation

## Slide 3
Status at the end of first phase
Euro-NCAP requirements.
Functional safety
  Hazard Analysis and Risk Assessment
  Safety goal and ASIL assignment
  Functional safety concept
  ASIL Decomposition and Decomposed FSR
Functional architecture
Document delivery

## Slide 4
2016
2017
Today
Nov
Dec
Jan
Feb
Mar
Project Kick Off
25.11.16
Project End
28.03.17
25/11/16 – 13/01/17
Phase 1: Functional Safety
26 days
23 days
55 days
12 days
43 days
Phase 2:
Design
Phase 3: Implementation
13.01.17
16.01.17
27.01.17
30.01.17
Project Timeline
1st Presentation to NXP
06.01.17
Holidays
Status meeting:NXP
20.01.17
Meeting
with Arash

## Slide 5
Status at the end of second phase
Milestones:
Use of CAFCR framework for system architecting
Analysis of existing Hardware
  Study hardware components
  Study communication networks
Hardware architecture proposals
Update safety concept
Document delivery
Progress |  | 
 | Delayed | 

## Slide 6: Planning for Phase 3
Short term goals ( next 2 weeks)
Interpretation of MobilEye data
Literature research on current lateral control strategies
Set up vehicle model in Matlab/Simulink
Research on real time prototyping environment
Long term goals
Develop lateral control strategy for ALC
Design and implement ALC software in car
Testing and validation with basic test cases
Update System Design Document
Presentation and demonstration
Running low level control algorithm on BlueBox
Implementation for switching between MobilEye
and HDR Mono camera

## Slide 7
2016
2017
Today
Jan
Feb
March
Start Phase 3
30.01.17
Phase 3:
Implementation
26 days
28.03.17
Predicted Arrival of Speedgoat
15nd Feb
Documentation Delivery
28th March
Project End
Planning for Phase 3
43 days
Testing
Vehicle Model
Literature Review
Comunication Setup
Simulation phase
Finalization phase
Controller Design
Demonstration & Presentation
28th March
Improvement
Prototype phase

## Slide 8: Limitation of Scope
Limitation of driving scenarios
  Highway, within specific restrictions (speed, road radius… etc)
Design Phase of the ISO26262
  not enough time, the time allocated for functional safety was used fully
Vision algorithm development
  Focus on control algorithm, and preparation for integration
  Use of Mobileye vision system for implementation
Development only on NXP Bluebox
  The Bluebox is not ready for the full system
  Reserve time for 1 integration test and error logging

## Slide 9: Risks
Uncertainity in the availability of hardware
  Estimated arrival of Real-Time target machine 15 Feb 2017
Reliance on Mobileye for vision

## Slide 10: Control Strategies
Controller |  | Simplicity (Implementation) | Computational Efficiency | Performance (Tracking) | Robustness
PID |  | ++ | ++ | - | -
Adaptive PID | Fuzzy Logic | -- | - | + | +
 | Neural Network | -- | -- | ++ | +
 | Minimum Variance | + | + | + | +
 | Nested | + | + | + | +
LQR |  | + | + | + | +
Robust Control |  | - | - | + | ++
H2 Optimal |  | - | - | + | +
Sliding Mode |  | -- | - | + | ++
MPC |  | -- | - | ++ | ++
Cost
Quality
Notes: Way too short

## Slide 11: Control System
Vehicle Model
Coefficient
Adapter
Controller

## Slide 12: Questions
?