## Slide 1
2016
2017
Today
Nov
Dec
Jan
Feb
Mar
Project Kick Off
25.11.16
Project End
28.03.17
25/11/16 – 13/01/17
Phase 1: Functional Safety
26 days
23 days
55 days
12 days
43 days
Phase 2:
Design
Phase 3: Implementation
13.01.17
16.01.17
27.01.17
30.01.17

## Slide 2
2016
2017
Today
Nov
Dec
Jan
Project Kick Off
25.11.16
25/11/16 – 13/01/17
Phase 1:
Functional Safety
26 days
13.01.17
NCAP Requirements
2nd Dec
CAFCR
9th Dec
HARA
14th Dec
FSR
20th Dec
Documentation
11th Jan
End – Phase 1