## Project Plan and Gantt
Project Management Dashboard
Project Name: | ALC
Project Status | On track
Broad level phases | tasks |  | Status | Priority | Status
Concept phase | Bycycle modelling | 42766 |  |  | In progress
Heading following
Literature survey: lateral control strategies
Control Strategies: Benchmarking, pitfalls
Lateral control stratey: proposals
Understanding communication with RTE
Setting up a basic communication channel for all signals
Understanding mobileye data
Setting up basic communication channel to detect lanes
Implementation | Model implementation
| determine ego state w.r.t. lanes |  |  |  | Not started
implement lateral controller to actively steer
Supervisor design
whole integration
Testing and validation | Create test vectors |  |  |  | Not started
simulation and validation
Vehicle level testing
Testing on NXP bluebox
Improvement | TBD |  |  |  | Not started
Demonstration | TBD |  |  |  | Not started
Presentation | Presentation for status update: 1 |  |  |  | Not started
| Presentation for status update: 2 |  |  |  | Not started
| Presentation for status update: 3 |  |  |  | Not started
Documentation | Document - Intermediate |  |  |  | Not started
Document - Final

## TaskTable
Task Table | [7 empty] | Broad level phases
Broad level phases | Tasks | Subtasks | Assigned To | Start | End | Days | Status | Start | End | days
Concept phase | Vehicle modelling | Bicycle modelling | Raymond, Sharad | 2017-01-31 | 2017-02-07 | 7 | In progress | 2017-01-31 | 2017-02-16 | 1900-01-15
|  | Heading following | Raymond, Sharad | 2017-01-31 | 2017-02-07 | 7 | In progress
| Lateral control strategy | Literature survey: lateral control strategies | Anshuman, Davide | 2017-01-31 | 2017-02-07 | 7 | In progress
|  | Benchmarking, pitfalls | Anshuman, Davide | 2017-01-31 | 2017-02-07 | 7 | In progress
|  | Lateral control stratey: proposals | Anshuman, Davide | 2017-02-03 | 2017-02-09 | 6 | Not started
| Prototyping with Real Time Environment | Understanding communication with RTE | TBD | 2017-02-10 | 2017-02-16 | 6 | Not started
|  | Setting up a basic communication channel for all signals | TBD | 2017-02-10 | 2017-02-16 | 6 | Not started
| Lane detection using Mobileye | Understanding mobileye data | TBD | 2017-02-10 | 2017-02-16 | 6 | Not started
|  | Setting up basic communication channel to detect lanes | TBD | 2017-02-10 | 2017-02-16 | 6 | Not started
Implementation | Implementation | Model implementation | Raymond, Sharad | 2017-02-03 | 2017-02-09 | 6 | Not started | 2017-02-03 | 2017-02-09 | 6
|  | determine ego state w.r.t. lanes | TBD | 2017-02-17 | 2017-02-27 | 10 | Not started | 2017-02-17 | 2017-03-06 | 1900-01-16
|  | implement lateral controller to actively steer | TBD | 2017-02-17 | 2017-02-27 | 10 | Not started
|  | Supervisor design | TBD | 2017-02-20 | 2017-02-27 | 7 | Not started
|  | whole integration | TBD | 2017-02-22 | 2017-03-06 | 12 | Not started
Testing and validation | System Testing | Create test vectors | TBD | 2017-02-27 | 2017-03-10 | 11 | Not started | 2017-02-27 | 2017-03-15 | 16
|  | simulation and validation | TBD | 2017-02-27 | 2017-03-10 | 11 | Not started
|  | Vehicle level testing | TBD | 2017-03-09 | 2017-03-14 | 5 | Not started
|  | testing on NXP bluebox | TBD | 2017-03-15 | 2017-03-15 | 0 | Not started
Improvement | Contineous Improvement | TBD | TBD | 2017-03-15 | 2017-03-24 | 9 | Not started | 2017-03-15 | 2017-03-24 | 9
Demonstration | Demonstration | TBD | TBD | 2017-03-24 | 2017-03-28 | 4 | Not started | 2017-03-24 | 2017-03-28 | 4
Presentation | Presentation | Presentation for status update: 1 | TBD | 2017-02-09 | 2017-02-10 | 1 | Not started | 2017-02-09 | 2017-02-10 | 1
|  | Presentation for status update: 2 | TBD | 2017-02-22 | 2017-02-24 | 2 | Not started | 2017-02-22 | 2017-02-24 | 2
|  | Presentation for status update: 3 | TBD | 2017-03-15 | 2017-03-17 | 2 | Not started | 2017-03-15 | 2017-03-17 | 2
Documentation | Documentation | Document - Intermediate | All | 2017-02-27 | 2017-02-28 | 1 | Not started | 2017-02-27 | 2017-02-28 | 1
|  | Document - Final | All | 2017-03-24 | 2017-03-28 | 4 | Not started | 2017-03-24 | 2017-03-28 | 4
| Launch |  |  | 2017-03-27 | 2017-03-28 | 1
Percentage of Tasks Complete
Complete
Overdue
In progress
Not Started
Budget
| Planned |  | 80000
| Actual |  | 50000
Pending Items
| Decisions |  | 0
| Actions |  | 0
| Change Requests |  | 0
Formulas:
Start = MIN([Start]:E12)
Start = MIN([Start])
End = MAX([End]:F12)
End = MAX([End])
days = [End]-[Start]